## REFERENCE_KEY
PROJECTS | NAME | REFERENCE KEY | TEAM | TAB
1 | THEMATIC REVIEW OF REFERRAL ARRANGEMENTS | RA | POLICY | OVERVIEW
2 | COMPENDIUM | C | POLICY | OVERVIEW
3 | COMPENSATION FUND | CF | MONITORING | OVERVIEW
N/A | COMPLETE | C | N/A | DAILY_TRACKER
N/A | IN PROGRESS | IP | N/A | DAILY_TRACKER

## OVERVIEW
Column Number | Tasks | Start Date | End Date | Duration- In Days*
1 | RA -DISCOVERY PHASE | 2026-01-13 | 2026-02-05
2 | RA- Read CLC Handbook | 2026-01-13 | 2026-01-28 | 3
3 | RA -Review Inspection logs | 2026-01-19 | 2026-02-05
4 | RA-Read the Project Plan | 2026-01-19 | 2026-01-26 | 1
5 | RA- Review monitoring team's Inspection logs for 2024 | 2026-01-28 | 2026-02-04 | 2
6 | RA- Review monitoring team's Inspection logs for 2025 | 2026-02-02 | 2026-02-04 | 2
7 | RA- Review monitoring team's Inspection logs for 2020 | 2026-06-05 | 2026-02-09 | 2
8 | RA- Review monitoring team's Inspection logs for 2021 | 2026-02-11 | 2026-02-12 | 2
9 | RA- Review monitoring team's Inspection logs for 2022 | 2026-02-16 | 2026-02-18 | 2
10 | RA- Review monitoring team's Inspection logs for 2023 | 2026-02-19 | 2026-02-25 | 2
11 | RA- Review Annual Regulatory Return for 2025 | 2026-02-02 | 2026-02-25 | 2
12 | RA- Review Annual Regulatory Return for 2024 | 2026-01-27 | 2026-02-02 | 2
13 | RA- ANALYSIS PHASE | 2026-01-28 | 2026-02-25 | 5
14 | RA- Questions and Feedback | 2026-01-28 | 2026-02-25 | 11
15 | RA -DOCUMENTATION PHASE | 2026-02-02 | 2026-03-12
16 | RA- Write Project Requirements Specification (PRS) | 2026-02-02 | 2026-02-04 | 2
17 | RA- Document results of Analysis phase | 2026-02-02 | 2026-02-26 | 11
18 | RA- Final Report for review & publication | 2026-03-02 | 2026-03-12 | 6
19 | CF - DISCOVERY PHASE | 2026-01-13 | 2026-03-19
20 | CF- Review Development Breakdown in the Master List | 2026-01-13 | 2026-01-19 | 2
21 | CF- Review Gaddes Noble paper files for 16 claimants | 2026-01-21 | 2026-03-30 | 10
22 | CF- ANALYSIS PHASE | 2026-01-19 | 2026-03-19
23 | CF- Scan paper files of 16 claimants sent by Gaddes Noble | 2026-01-22 | 2026-02-26 | 9
24 | CF - Download scanned files to relevant folder | 2026-01-22 | 2026-02-26 | 9
25 | CF - Download files from Leap database to relevant folders | 2026-02-12 | 2026-02-26 | 5
26 | CF- Cross check all files against master list and amend where necessary | 2026-01-19 | 2026-03-19 | 15
27 | CF -DOCUMENTATION PHASE | 2026-03-19 | 2026-03-26
28 | CF -Prepare final report on claims for Monitoring team review | 2026-03-19 | 2026-04-02 | 6
29 | C- DISCOVERY PHASE | 2026-01-14 | 2026-02-26
30 | C - Review of Corporate register of Policies | 2026-01-26 | 2026-02-16 | 4
31 | C - Write PRS – Requirements spec of end goal, business requirements and scope | 2026-02-16 | 2026-02-26 | 6
32 | C- ANALYSIS PHASE | 2026-01-28 | 2026-03-12
33 | C- Gap Analysis of codes on CLC website against the Corporate Register | 2026-01-14 | 2026-02-23 | 6
34 | C -DOCUMENTATION PHASE | 2026-02-23 | 2026-03-26
35 | C- Update the Corporate Register to add the missing Policy codes from the CLC Code of Conduct. | 2026-02-23 | 2026-03-30 | 15
36 | C-Review Regulatory Standards ppt – Governance, Leadership and Operational and assess how the various codes map to each level, highlight any gaps and add more information where appropriate | 2026-01-14 | 2026-03-30 | 20
37 | C- Prepare Compendium report for review | 2026-03-12 | 2026-04-08 | 10
This is an estimate of duration rather than effort- as it also includes any overlapping tasks.
|  | 46035 | 46120

## DAILY_TRACKER
Column Number | Dates | RA- Read CLC Handbook | CF- Review Development Breakdown in the Master List | RA -Review Inspection logs | CF- Review Gaddes Noble paper files for 16 claimants | RA- Review monitoring team's Inspection logs for 2025 | RA- Review monitoring team's Inspection logs for 2020 | RA- Review monitoring team's Inspection logs for 2022 | RA- Review monitoring team's Inspection logs for 2023 | RA- Review Annual Regulatory Return for 2025 | CF- Cross check all files against master list and amend where necessary | RA- Document results of Analysis phase | RA- Final Report for review & publication | CF- Scan paper files of 16 claimants sent by Gaddes Noble | CF - Download scanned files to relevant folder | RA-Read the Project Plan | C - Review of Corporate register of Policies | RA- Review monitoring team's Inspection logs for 2024 | CF - Download files from Leap database to relevant folders | RA- Review Annual Regulatory Return for 2024 | CF -Prepare final report on claims for Monitoring team review | RA- Write Project Requirements Specification (PRS) | RA- Questions and Feedback | C - Write PRS – Requirements spec of end goal, business requirements and scope | C- Gap Analysis of codes on CLC website against the Corporate Register | C- Update the Corporate Register to add the missing Policy codes from the CLC Code of Conduct. | C-Review Regulatory Standards ppt – Governance, Leadership and Operational and assess how the various codes map to each level, highlight any gaps and add more information where appropriate | C- Prepare Compendium report for review
1 | 2026-01-13 | IP | IP | [22 empty] | IP
2 | 2026-01-14 | IP | [23 empty] | IP
3 | 2026-01-16
4 | 2026-01-19 |  | C | IP | [6 empty] | IP |  |  |  |  | IP
5 | 2026-01-21 |  |  |  | IP | [5 empty] | IP
6 | 2026-01-22 |  |  |  | IP | [8 empty] | IP | IP
7 | 2026-01-26 | IP |  |  | IP | [9 empty] | IP | C
8 | 2026-01-27 | [18 empty] | IP
9 | 2026-01-28 | [16 empty] | IP |  |  |  |  | IP
10 | 2026-02-02 | IP |  | IP | IP
11 | 2026-02-04
12 | 2026-02-05
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Staff Day - From 1300-1700